## Test Cases
Product Name | Excel Extensions (Add-ins) | Test Case Start Date | 2023-10-02 | TC Execution Start Date | 2023-12-12 | TEST CASES |  |  |  | TC Execution Start Date | 2023-12-13 | TEST CASES |  |  |  | TC Execution Start Date | 2023-12-13 | TEST CASES |  |  |  | TC Execution Start Date | 2023-08-02 | TEST CASES
Developer Name (VSTO) | Zahid Hasan | Test Case End Date | 2023-10-02 | TC Execution End Date | 2023-12-12 | PASS |  | 13 |  | TC Execution End Date | 2023-12-13 | PASS |  | 3 |  | TC Execution End Date | 2023-12-13 | PASS |  | 3 |  | TC Execution End Date | 2023-08-03 | PASS |  | 0
Developer Name (Web) | Atik Ullah Khan | Test Case Developed by | Rabeya Islam | TC Executed by | Nujat Tasnim | FAIL |  | 0 |  | TC Executed by | Nujat Tasnim | FAIL |  | 1 |  | TC Executed by | Nujat Tasnim | FAIL |  | 1 |  | TC Executed by |  | FAIL |  | 0
|  | Test Case Reviewed by | Rabeya Islam | Test Environment | Excel 365 - Windows 10 | Partially Failed |  | 9 |  | Test Environment | Excel 365 - Windows 10 | Partially Failed |  | 17 |  | TC Execution Reviewed by | Rabeya Islam | Partially Failed |  | 17 |  | TC Execution Reviewed by | Rabeya Islam | Partially Failed |  | 0
|  |  |  | TC Execution Reviewed by | Rabeya Islam | Block/ Skip |  | 0 |  | TC Execution Reviewed by | Rabeya Islam | Block/ Skip |  | 1 |  |  |  | Block/ Skip |  | 1 |  |  |  | Block/ Skip |  | 0
[6 empty] | Not Executed |  | 0 |  |  |  | Not Executed |  | 0 |  |  |  | Not Executed |  | 0 |  |  |  | Not Executed |  | 0
[6 empty] | Total |  | 22 |  |  |  | Total |  | 22 |  |  |  | Total |  | 22 |  |  |  | Total |  | 0
|  |  |  | Excel VSTO Add-ins | [5 empty] | Excel Office Web Add-ins (on Desktop) | [5 empty] | Excel Office Add-ins (on 365 online) | [5 empty] | Excel Office Add-ins (on MAC)
Test Case ID | Action - Test Case | Expected Output |  | Actual Output | Screenshot - Video | Test Status | Notes / Feedback |  | Coder's Feedback | Actual Output | Screenshot - Video | Test Status | Notes / Feedback |  | Coder's Feedback | Actual Output | Screenshot - Video | Test Status | Notes / Feedback |  | Coder's Feedback | Actual Output | Screenshot - Video | Test Status | Notes / Feedback |  | Coder's Feedback
Prereq. | N/A
TC01 | Source Range (Mouse selection) > OK. | Hide every cell except the selected cell range. For Web - Will show confirmation message "Scroll area is set successfully" |  | As expected. |  | Pass |  |  |  | Showed confirmation msg "Everything except the selected range has been hidden successfully.", | Specify Scroll Area- TC01.mp4 | Partially Failed | Please make sure it shows the exact confirmation msg. |  | Solved | Showed confirmation msg "Everything except the selected range has been hidden successfully.", | Specify Scroll Area- TC01.mp4 | Partially Failed | Please make sure it shows the exact confirmation msg. |  | Solved |  |  | Ready to Test |  |  | Not Solved
TC01.1 | Source Range (by typing) > OK. | Hide every cell except the selected cell range. For Web - Will show confirmation message "Scroll area is set successfully" |  | As expected. |  | Pass |  |  |  | Showed confirmation msg "Everything except the selected range has been hidden successfully.". | Specify Scroll Area- TC01.1.mp4 | Partially Failed | Please make sure it shows the exact confirmation msg. |  | Solved | Showed confirmation msg "Everything except the selected range has been hidden successfully.". | Specify Scroll Area- TC01.1.mp4 | Partially Failed | Please make sure it shows the exact confirmation msg. |  | Solved |  |  | Ready to Test |  |  | Not Solved
TC01.2 | VSTO- Source Range (Manual selection) > OK. | Hide every cell except the selected cell range. For Web - Will show confirmation message "Scroll area is set successfully" |  | As expected. |  | Pass |  |  |  | N/A |  | Block/ Skip |  |  |  | N/A |  | Block/ Skip | [5 empty] | Ready to Test |  |  | Not Solved
TC01.3 | Source Range (Type C5:E12) > OK. | Hide every cell except the selected cell range. For Web - Will show confirmation message "Scroll area is set successfully" |  | As expected. |  | Pass |  |  |  | Showed confirmation msg "Everything except the selected range has been hidden successfully.". | Specify Scroll Area- TC01.3.mp4 | Partially Failed | Please make sure it shows the exact confirmation msg. |  | Solved | Showed confirmation msg "Everything except the selected range has been hidden successfully.". | Specify Scroll Area- TC01.3.mp4 | Partially Failed | Please make sure it shows the exact confirmation msg. |  | Solved |  |  | Ready to Test |  |  | Not Solved
TC01.4 | Source Range (Type C13:B5) > OK. | Hide every cell except the selected cell range. For Web - Will show confirmation message "Scroll area is set successfully" |  | As expected. |  | Pass |  |  |  | Showed confirmation msg "Everything except the selected range has been hidden successfully.". | Specify Scroll Area- TC01.4.mp4 | Partially Failed | Please make sure it shows the exact confirmation msg. |  | Solved | Showed confirmation msg "Everything except the selected range has been hidden successfully.". | Specify Scroll Area- TC01.4.mp4 | Partially Failed | Please make sure it shows the exact confirmation msg. |  | Solved |  |  | Ready to Test |  |  | Not Solved
TC01.5 | Source Range (B7:D14,E7:G14) > OK. | Hide every cell except the selected cell range. For Web - Will show confirmation message "Scroll area is set successfully" |  | As expected. |  | Pass |  |  |  | Showed confirmation msg "Everything except the selected range has been hidden successfully.". |  | Partially Failed | Please make sure it shows the exact confirmation msg. |  | Solved | Showed confirmation msg "Everything except the selected range has been hidden successfully.". |  | Partially Failed | Please make sure it shows the exact confirmation msg. |  | Solved |  |  | Ready to Test |  |  | Not Solved
TC01.6 | Source Range (B7:D14,F7:G14) > OK. | Hide every cell except the selected cell range. For Web - Will show confirmation message "Scroll area is set successfully" |  | As expected. |  | Pass |  |  |  | Showed confirmation msg "Everything except the selected range has been hidden successfully.". | Specify Scroll Area- TC01.6.mp4 | Partially Failed | Please make sure it shows the exact confirmation msg. |  | Solved | Showed confirmation msg "Everything except the selected range has been hidden successfully.". | Specify Scroll Area- TC01.6.mp4 | Partially Failed | Please make sure it shows the exact confirmation msg. |  | Solved |  |  | Ready to Test |  |  | Not Solved
TC01.7 | Source Range (B7:D14,F7:G14,H7:H14) > OK. | Hide every cell except the selected cell range. For Web - Will show confirmation message "Scroll area is set successfully" |  | As expected. |  | Pass |  |  |  | Showed confirmation msg "Everything except the selected range has been hidden successfully.". | Specify Scroll Area- TC01.7.mp4 | Partially Failed | Please make sure it shows the exact confirmation msg. |  | Solved | Showed confirmation msg "Everything except the selected range has been hidden successfully.". | Specify Scroll Area- TC01.7.mp4 | Partially Failed | Please make sure it shows the exact confirmation msg. |  | Solved |  |  | Ready to Test |  |  | Not Solved
TC01.8 | Source Range (B7:D14,B16:D17) > OK. | Hide every cell except the selected cell range. For Web - Will show confirmation message "Scroll area is set successfully" |  | As expected. |  | Pass |  |  |  | Showed confirmation msg "Everything except the selected range has been hidden successfully.". | Specify Scroll Area- TC01.8.mp4 | Partially Failed | Please make sure it shows the exact confirmation msg. |  | Solved | Showed confirmation msg "Everything except the selected range has been hidden successfully.". | Specify Scroll Area- TC01.8.mp4 | Partially Failed | Please make sure it shows the exact confirmation msg. |  | Solved |  |  | Ready to Test |  |  | Not Solved
TC01.9 | Source Range (B7:D14,B16:D17,B19:D20) > OK. | Hide every cell except the selected cell range. For Web - Will show confirmation message "Scroll area is set successfully" |  | As expected. |  | Pass |  |  |  | Showed confirmation msg "Everything except the selected range has been hidden successfully.". | Specify Scroll Area- TC01.9.mp4 | Partially Failed | Please make sure it shows the exact confirmation msg. |  | Solved | Showed confirmation msg "Everything except the selected range has been hidden successfully.". | Specify Scroll Area- TC01.9.mp4 | Partially Failed | Please make sure it shows the exact confirmation msg. |  | Solved |  |  | Ready to Test |  |  | Not Solved
TC01.10 | Source Range (B5) > OK. | Will show notification "Do you really want to hide everything except one/ two/ three/ four cell/'s?" If yes, hide every cell except the selected cell range. If no, close the add-in. For Web - Will show confirmation message "Scroll area is set successfully" |  | Showed notification "Do you really want to hide everything except 1 cells. If yes, hide every cell except the selected cell range. If no, close the add-in." | Specify Scroll Area- TC01.10.mp4 | Partially Failed | Please make sure it shows the exact notification. (Do you really want to hide everything except 1 cell? If yes, hide every cell except the selected cell range. If no, close the add-in.) |  | Not Solved | Showed notification "Do you really want to hide everything except 1 cell? Confirm/Cancel". After clicking Confirm, showed confirmation msg "Everything except the selected range has been hidden successfully.". | Specify Scroll Area- TC01.10.mp4 | Partially Failed | Please make sure it shows the exact confirmatrion msg. |  | Solved | Showed notification "Do you really want to hide everything except 1 cell? Confirm/Cancel". After clicking Confirm, showed confirmation msg "Everything except the selected range has been hidden successfully.". | Specify Scroll Area- TC01.10.mp4 | Partially Failed | Please make sure it shows the exact confirmatrion msg. |  | Solved |  |  | Ready to Test |  |  | Not Solved
TC01.11 | Source Range (B5:B6) > OK. | Will show notification "Do you really want to hide everything except one/ two/ three/ four cell/'s? If yes, hide every cell except the selected cell range. If no, close the add-in. For Web - Will show confirmation message "Scroll area is set successfully" |  | Showed notification "Do you really want to hide everything except 2 cells. If yes, hide every cell except the selected cell range. If no, close the add-in." | Specify Scroll Area- TC01.11.mp4 | Partially Failed | Please make sure it shows the exact notification. (Do you really want to hide everything except 2 cells? If yes, hide every cell except the selected cell range. If no, close the add-in.) |  | Not Solved | Showed notification "Do you really want to hide everything except 2 cells? Confirm/Cancel". After clicking Confirm, showed confirmation msg "Everything except the selected range has been hidden successfully.". | Specify Scroll Area- TC01.11.mp4 | Partially Failed | Please make sure it shows the exact confirmatrion msg. |  | Solved | Showed notification "Do you really want to hide everything except 2 cells? Confirm/Cancel". After clicking Confirm, showed confirmation msg "Everything except the selected range has been hidden successfully.". | Specify Scroll Area- TC01.11.mp4 | Partially Failed | Please make sure it shows the exact confirmatrion msg. |  | Solved |  |  | Ready to Test |  |  | Not Solved
TC01.12 | Source Range (B5:C6) > OK. | Will show notification "Do you really want to hide everything except one/ two/ three/ four cell/'s? If yes, hide every cell except the selected cell range. If no, close the add-in. For Web - Will show confirmation message "Scroll area is set successfully" |  | Showed notification "Do you really want to hide everything except 4 cells. If yes, hide every cell except the selected cell range. If no, close the add-in." | Specify Scroll Area- TC01.12.mp4 | Partially Failed | Please make sure it shows the exact notification. (Do you really want to hide everything except 4 cells? If yes, hide every cell except the selected cell range. If no, close the add-in.) |  | Not Solved | Showed notification "Do you really want to hide everything except 4 cells? Confirm/Cancel". After clicking Confirm, showed confirmation msg "Everything except the selected range has been hidden successfully.". | Specify Scroll Area- TC01.12.mp4 | Partially Failed | Please make sure it shows the exact confirmatrion msg. |  | Solved | Showed notification "Do you really want to hide everything except 4 cells? Confirm/Cancel". After clicking Confirm, showed confirmation msg "Everything except the selected range has been hidden successfully.". | Specify Scroll Area- TC01.12.mp4 | Partially Failed | Please make sure it shows the exact confirmatrion msg. |  | Solved |  |  | Ready to Test |  |  | Not Solved
TC01.13 | Source Range (B5:C5) > OK. | Will show notification "Do you really want to hide everything except one/ two/ three/ four cell/'s? If yes, hide every cell except the selected cell range. If no, close the add-in. For Web - Will show confirmation message "Scroll area is set successfully" |  | Showed notification "Do you really want to hide everything except 2 cells. If yes, hide every cell except the selected cell range. If no, close the add-in." | Specify Scroll Area- TC01.13.mp4 | Partially Failed | Please make sure it shows the exact notification. (Do you really want to hide everything except 2 cells? If yes, hide every cell except the selected cell range. If no, close the add-in.) |  | Not Solved | Showed notification "Do you really want to hide everything except 2 cells? Confirm/Cancel". After clicking Confirm, showed confirmation msg "Everything except the selected range has been hidden successfully.". | Specify Scroll Area- TC01.13.mp4 | Partially Failed | Please make sure it shows the exact confirmatrion msg. |  | Solved | Showed notification "Do you really want to hide everything except 2 cells? Confirm/Cancel". After clicking Confirm, showed confirmation msg "Everything except the selected range has been hidden successfully.". | Specify Scroll Area- TC01.13.mp4 | Partially Failed | Please make sure it shows the exact confirmatrion msg. |  | Solved |  |  | Ready to Test |  |  | Not Solved
TC01.14 | Source Range (empty) > OK. | Error message "Please select a valid source range.". |  | Showed warning "Please provide source range." | Specify Scroll Area- TC01.14.png | Partially Failed | Please show the exact warning msg. |  | Solved | Showed warning "Select a valid source range." | Specify Scroll Area- TC01.14.png | Partially Failed | Please show the exact warning msg. |  | Solved | Showed warning "Select a valid source range." | Specify Scroll Area- TC01.14.png | Partially Failed | Please show the exact warning msg. |  | Solved |  |  | Ready to Test |  |  | Not Solved
TC01.15 | Source Range (B5:) > OK. | Error message "Please select a valid source range.". |  | Showed warning "Please provide a valid source range." | Specify Scroll Area- TC01.15.png | Partially Failed | Please show the exact warning msg. |  | Solved | Showed warning "Select a valid source range." | Specify Scroll Area- TC01.15.png | Partially Failed | Please show the exact warning msg. |  | Solved | Showed warning "Select a valid source range." | Specify Scroll Area- TC01.15.png | Partially Failed | Please show the exact warning msg. |  | Solved |  |  | Ready to Test |  |  | Not Solved
TC01.16 | Source Range (/:) > OK. | Error message "Please select a valid source range.". |  | Showed warning "Please provide a valid source range." |  | Partially Failed | Please show the exact warning msg. |  | Solved | Showed warning "Select a valid source range." |  | Partially Failed | Please show the exact warning msg. |  | Solved | Showed warning "Select a valid source range." |  | Partially Failed | Please show the exact warning msg. |  | Solved |  |  | Ready to Test |  |  | Not Solved
TC01.17 | Source Range (B7:D14,F7:G13) > OK. | Error message "Multiple selection is not possible with this source range.". |  | Same as expected. |  | Pass |  |  |  | As Expected. |  | Pass |  |  |  | As Expected. |  | Pass | [5 empty] | Ready to Test |  |  | Not Solved
TC01.18 | Source Range (B7:D14,B16:D17,F7:G14) > OK. | Error message "Multiple selection is not possible with this source range.". |  | Same as expected. |  | Pass |  |  |  | As Expected. |  | Pass |  |  |  | As Expected. |  | Pass | [5 empty] | Ready to Test |  |  | Not Solved
TC02 | Source Range (B5:B6) > Create a copy of the original worksheet > OK. | Will show notification "Do you really want to hide everything except one/ two/ three/ four cell/'s? If yes, hide every cell except the selected cell range. If no, close the add-in." Also it will craete a copy of the current worksheet. For Web - Will show confirmation message "Scroll area is set successfully" |  | Showed notification "Do you really want to hide everything except 2 cells. If yes, hide every cell except the selected cell range. If no, close the add-in."; also created a copy of the original worksheet as expected. | Specify Scroll Area- TC02.mp4 | Partially Failed | Please make sure it shows the exact notification. (Do you really want to hide everything except 2 cells? If yes, hide every cell except the selected cell range. If no, close the add-in.) |  | Not Solved | Showed warning "Do you really want to hide everything except 2 cells? Confirm/ Cancel". After clicking Confirm, showed confirmation msg "Everything except the selected ranges has been hidden successfully."; Also didn't find "Create a copy of the original worksheet" option. | Specify Scroll Area- TC02.mp4 | Fail | Please make sure it has option called "Create a copy of the original worksheet" and shows the exact confirmation msg. |  | Solved | Showed warning "Do you really want to hide everything except 2 cells? Confirm/ Cancel". After clicking Confirm, showed confirmation msg "Everything except the selected ranges has been hidden successfully."; Also didn't find "Create a copy of the original worksheet" option. | Specify Scroll Area- TC02.mp4 | Fail | Please make sure it has option called "Create a copy of the original worksheet" and shows the exact confirmation msg. |  | Solved |  |  | Ready to Test |  |  | Not Solved
TC03 | Source Range (B5:C5) > Create a copy of the original worksheet > ENTER. | Will show notification "Do you really want to hide everything except one/ two/ three/ four cell/'s? If yes, hide every cell except the selected cell range. If no, close the add-in." Also it will craete a copy of the current worksheet. For Web - Will show confirmation message "Scroll area is set successfully" |  | Showed notification "Do you really want to hide everything except 2 cells. If yes, hide every cell except the selected cell range. If no, close the add-in."; also created a copy of the original worksheet as expected. | Specify Scroll Area- TC03.mp4 | Partially Failed | Please make sure it shows the exact notification. (Do you really want to hide everything except 2 cells? If yes, hide every cell except the selected cell range. If no, close the add-in.) |  | Not Solved | Enter didn't work; Also didn't find "Create a copy of the original worksheet" option. | Specify Scroll Area- TC03.mp4 | Partially Failed | Please make sure Enter works as well as shows the exact confirmation msg. |  | Not Solved | Enter didn't work; Also didn't find "Create a copy of the original worksheet" option. | Specify Scroll Area- TC03.mp4 | Partially Failed | Please make sure Enter works as well as shows the exact confirmation msg. |  | Not Solved |  |  | Ready to Test |  |  | Not Solved
TC04 | Source Range (B5:C5) > Cancel. | It should cancel the process and unload the add-in. |  | Same as expected. |  | Pass |  |  |  | As Expected. |  | Pass |  |  | Solved | As Expected. |  | Pass |  |  | Solved |  |  | Ready to Test |  |  | Not Solved
TC05 | Open "Specify Scroll Area" add-in. | Verify if first option of the selection grp is selceted by default or not. |  | Same as expected. |  | Pass |  |  |  | Same as expected. |  | Pass |  |  |  | Same as expected. |  | Pass
TC06 | Ctrl+Z | It will undo the changes. |  | Didn't undo the changes. |  | Fail | Please make sure it undo the changes. |  | Not Solved | Didn't undo the changes. |  | Fail | Please make sure it undo the changes. |  | Not Solved | Didn't undo the changes. |  | Fail | Please make sure it undo the changes. |  | Not Solved

## Bug Report
Bug ID | Summary | Description | Related Test Cases | Notes / Feedback | Coder's Feedback
Excel VSTO Add-ins
BUG01 | Didn't able to show exact notification for small number of cell selection. | When the source range is one/two/three/four cells, doesn't show the exact notification msg. | TC01.10, TC01.11, TC01.12,TC01.13, TC02, TC03 |  | Not Solved
BUG02 | Didn't able to show exact warning msg. | When the source range is invalid or empty, it doesn't show exact warning msg. | TC01.14, TC01.15, TC01.16 |  | Not Solved
BUG03 | Create a copy of the original worksheet is not selected by default. | Create a copy of the original worksheet should be selected by default. | TC05 |  | Not Solved
BUG04 | Ctrl+Z | Didn't undo the changes. | TC06 |  | Not Solved
Excel Office Add-ins (on Desktop)
BUG01 | "Create a copy of the original worksheet" option is not found and not selected by default. | "Create a copy of the original worksheet" option is not found and this option should be selected by default. | TC04, TC05 |  | Not Solved
BUG02 | Didn't show exact confirmation msg. | When we put valid inputs and after successful execution, it doesn't show exact confirmation msg. | TC01, TC01.1, TC01.3, TC01.4, TC01.5, TC01.6, TC01.7, TC01.8, TC01.9, TC01.10, TC01.11, TC01.12, TC01.13,TC02, |  | Not Solved
BUG03 | Didn't able to show exact warning msg. | When the source range is invalid or empty, it doesn't show exact warning msg. | TC01.14, TC01.15, TC01.16 |  | Not Solved
BUG04 | Enter didn't work. | When we put valid inputs and press ENTER, it doesn't work. | TC03 |  | Not Solved
BUG05 | Ctrl+Z | Didn't undo the changes. | TC06 |  | Not Solved
Excel Office Add-ins (on 365 online)
BUG01 | "Create a copy of the original worksheet" option is not found and not selected by default. | "Create a copy of the original worksheet" option is not found and this option should be selected by default. | TC04, TC05 |  | Not Solved
BUG02 | Didn't show exact confirmation msg. | When we put valid inputs and after successful execution, it doesn't show exact confirmation msg. | TC01, TC01.1, TC01.3, TC01.4, TC01.5, TC01.6, TC01.7, TC01.8, TC01.9, TC01.10, TC01.11, TC01.12, TC01.13,TC02, |  | Not Solved
BUG03 | Didn't able to show exact warning msg. | When the source range is invalid or empty, it doesn't show exact warning msg. | TC01.14, TC01.15, TC01.16 |  | Not Solved
BUG04 | Enter didn't work. | When we put valid inputs and press ENTER, it doesn't work. | TC03 |  | Not Solved
BUG05 | Ctrl+Z | Didn't undo the changes. | TC06 |  | Not Solved
Excel Office Add-ins (on MAC)
BUG01 |  |  |  |  | Not Solved
BUG02 |  |  |  |  | Not Solved
BUG03 |  |  |  |  | Not Solved

## UI Report
UI ID | Description | Screenshot | Coder's Feedback
Excel VSTO Add-ins
UI01 |  |  | Not Solved
UI02 |  |  | Not Solved
UI03 |  |  | Not Solved
Excel Office Add-ins (on Desktop)
UI01 | Create a copy of the original worksheet | Specify Scroll Area- UI01.png | Not Solved
UI02 | OK | Specify Scroll Area- UI02.png | Not Solved
UI03 | Cancel | Specify Scroll Area- UI03.png | Not Solved
Excel Office Add-ins (on 365 online)
UI01 | Create a copy of the original worksheet | Specify Scroll Area- UI01.png | Not Solved
UI02 | OK | Specify Scroll Area- UI02.png | Not Solved
UI03 | Cancel | Specify Scroll Area- UI03.png | Not Solved
Excel Office Add-ins (on MAC)
UI01 |  |  | Not Solved
UI02 |  |  | Not Solved
UI03 |  |  | Not Solved